## MVP thoughts
Highlights of the minimum viable product features
The minimum viable product (MVP) for a modern insurance platform serving RIAs, insurance brokers, and HNW clients should focus on core workflows that prove user value and gather feedback. The initial build V0 needs to be ready in 3 months, balancing functionality with speed to test core product-market fit. In addition within the 3 months, we need to build a clickable demo that showcases the UX described in the combined V0 and V1 features below.
RIA/ WEALTH MANAGER
MVP
# | Features | V0 | V1 | V2 | Comments
V2: Build a HNW app that RIAs can download and onboard themselves to access everything they need.
1 | Learn about PPLI/PPA (answers what is this, how does it work, why must it be part of the RIA's strategy, when is it best to introduce this/deploy it). We need to have customer facing materials they can send to HNWIs | x | x | x | V0: can be in google docs for RIAs to access easily. We will provide all the content. Just need to figure out the best way to make it easy for the RIA to get this while they are on their internal system, etc.
V1: Microsite or Portal that has content to view and consume by RIAs. It will have customer facing docs to print, and/or send to RIA’s clients. Ideally should be designed to ultimately integrate with the RIA’s investment platform. V1 will not yet be integrated. V2: integrated into an app
2 | Inforce Book Analysis Tool to help RIAs identify the clients that are best candidates for PPLI/PPA; and within that prioritize them for action. | x | x | x | V0: Have a Microsite or Portal –RIA logs into portal to import their client list (exportable file coming from their system of record contain key variables to help assess RIA’s opportunity for PPLI/PPA. The RIA will import into portal, answer probing questions and drop in assumptions that will be prompted by AI. The output will be to identify a prioritized list of clients to sell them a PPLI / PPA.
|  |  |  | x | V0: The analysis will simulate scenarios to help the RIA determine how much is prudent to invest in this instrument; how the client was ‘qualified’ for participation. The tool needs to help the RIA be confident about conveying this investment strategy, along with typical objections and rebuttals. So once they have their prioritized list, they need to take action (call, run email/SMS/ campaign. they should come back to this list to identify dispositions (is this CRM lite?) -integrate with email?
V1: will be more advanced, more professional looking and ideally integrated into the portal. Also, CRM integration needs to be contemplated if advisor already has a CRM; or a CRM lite needs to be built along with acces to marketing automation ( tools Hubspot? WealthBox?)
v2: Gen AI scripts and recommendations provided; integrations with other tools like Hubspot, WealthBox)
3 | Help RIAs identify how much to put into the PPPL/PPA strategy and simulate performance with tax efficient strategies. | x |  | x | V0: we will give you a financial model that will ask for inputs and deliver outputs to be shared with the RIA. V2: build this into the app.
4 | Use AI to prefill an intake to get an illustration | x | x | x | V0: Find a way to deliver 2 views of illustration (insurance oriented vs. investment oriented). V2: integrate this into the HNW app
5 | Drop in slides into pitch deck for RIA to use | x |  | x | V0: handle manually. V2: deck to be created automatically based on conditions established by RIA, and scenarios run by RIAs.
6 | Client agrees on new PPLI strategy; now RIA initiates their workflow onto their system of record (onboards new client or updates client profile; handles their or our insurance suitability? con; auto passes to broker, instructing client to gather all existing insurance information. |  | x | x | V1: Our Process should provide general guidance to RIA as to how to set up, pass to broker and what to expect. Also, they need to decide who takes the lead getting the insurance documents. Guidance to stress RIA/broker get Key documents in original source (give them a checklist). Broker meeting is set and brokers uploads document into a digital vault (w/ military grade security). docs must be securely access by all whoj support the HNW client. central access needs to allow RIA, broker and client to access. V2: this is integrated into the app (blockchain?)
V2: onboarding should ultimately be integrated into the app (consider blockchain?). Anything uploaded keeps audit trail and permissions history.
7 | Auto Progress notification: RIAs get key updates on progress, until (final) summary report is generated. | x | x | x | V0: manual? V1: progress bar in portal? V2: integrated into the app
8 | Once Life or annuity application & UW are complete, final summary report automatically comes to RIA. | x | x | x | V0: manual? V1: AI auto generates; V2: integrated into HNW app
9 | Ability to chat across roles (RIA to broker; RIA to client; client to both RIA and/or broker) | x | x | x | V0: integrate with their google email? V1: sms/chat built into portal. V2: integrated into app
10 | See an RIA Dashboard with all activity at a glance. Total AUM invested into the PPL/PPA strategies, which investment strategies, which carriers are behind this, what is the performance of those assets relative to what the initial plans were, extract data to help them prepare for client updates and reviews. | x | x | x | V0: some basic summary. V1: integratged into portal. V2:integrated into app
11 | Enable RIA to jot down key notes on client / broker interaction and get a nudge, alert and set notifications for actions / special instruction. | x | x | x | V0: some basic summary. V1: integratged into portal. V2:integrated into app
12 | Robust reporting / visualilzations to allow the RIA to sent updates to their clients with summary of what's going on with tax advanged strategies This needs to align with how investment strategies are profiled, and spoken about to make the RIA proud of using our tech. | x | x | x | V0: some basic summary. V1: integratged into portal. V2:integrated into app
BROKER (INSURANCE AGENT)
MVP
# | Features | V0 | V1 | V2 | Comments
V2: Build a HNW app that RIAs can download and onboard themselves to access everything they need.
1 | Access same collateral as RIA to become aware of new PPLI/PPA strategy, learn or get refresher. | x | x | x | V0: can be in google docs for RIAs to access easily. We will provide all the content. Just need to figure out the best way to make it easy for the RIA to get this while they are on their internal system, etc.
| Learn about PPLI/PPA – what, how, why, when; have customer facing materials they can send to HNWIs or share with attorneys, CPAs |  |  |  | V1: Microsite or Portal that has content to view and consume by broker/agents. It will have customer facing docs to print, and/or send to RIA’s clients. While this will ultimately integrate with the RIA’s investment platform, for the broker side of this, this feature can just leverage what is done for the RIA. V2: consider special features for broker specific learning needs in their own portal. Need broker feedback.
2 | Be able to see the automated pitch deck AI sent to RIA and be able to comment to help with initial PPLI/PPA intro to the HNWI. | x |  | x | V0: broker can get a copy of what the RIA receives and via email can respond/provide thoughts to RIA. V2: integrated into the app
3 | Client agrees on concept; now broker takes the lead. Uploads insurance Policies and any other suitability forms into digital vault / platform. | x | x | x | Key documents in original source are stored in military grade security and available for reference. Anything uploaded keeps audit trail (who uploaded, etc). V0: this is manually uploaded? V1: integrated in portal? V2: built into the HNW app. (blockchain)
4 | Broker’s sales pitch is auto created and insurance and coverage gaps are delivered for agent/broker to consider and adjust deck. | x |  | x | V0: manually created V3: integrated and auto generated using GenAI;
5 | Pipeline: See their inbox with new requests for PPLI or PPA to mobilize. Assign the work (to other agents) with priority level. Be able to see their full pipeline, see preliminary underwriting and rationale (based on an algorithm + human in the loop). | x | x | x | V0: Microsite? Portal? – brokers will see their pipeline and stage of the sales process with the HNW client and based on an algorithm see a prelim underwriting decision, as well as which carriers are best suited to place this business with. As it progresses with the illustration, quotes, applications, etc, it moves to a "case management view". This gets further improved in V1 and V2. | *
6 | Centralized eApp | x |  |  | V0: Microsite? Portal? – Using the data compiled from existing policies as well as discussions with HNWI, the AI prefills data input to do an illustration and continues to produce a centralized application, from which the AI recommends the best carrier and policy to put through based on specific criteria inputed by the broker. Broker submits e-app to carrier. | *
7 | Case management | x |  | x | V0: As it progresses with the illustration, applications, and EHR/labs are ordered, broker needs a case management view, with ability to integrate email to correspond with the carrier's UW team. V2: chat feature to be integrated into an app. | *
8 | Chat feature for messaging with carrier's team. Broker sees case management dashboard where they can chat with the carrier’s UW team to see what’s open and how to address gaps/delays, etc. RIAs gets key updates on progress, until (final) summary report. | x |  | x | V0: integrate email and communicate that way, but keep a record of the exchange in notes? V2: integrate it in the HNW app
9 | Enable Broker to push out the final illustration to RIA to keep him informed and summarize the gameplan with the carrier (high level). | x | x | x | v0: do this manually. v1: integrate into portal? V2: build into the HNW app. Have 2 views of illustration (insurance oriented vs. investment oriented)
10 | Auto receive final carrier policies and store in client vault | x |  |  |  | *
11 | Once Life or annuity UW are complete, final summary report automatically created (sent to RIA and potentially their client, if RIA set it up as such) | x |  | x | V0: manually create and distribute? V3: integrated into the app
12 | Ability to securely msg/chat across roles (RIA to broker; RIA to client; client to both RIA and/or broker) | x |  | x |  | *
13 | Broker to see other sales opportunities (based on holdings? Or based on other insurance documents collected) so he can tee up talking points for RIA , and send to him. | x | x | x | V0: handle manually; V1 and V2 add more sophistication and integrate into portal/app
14 | See Broker dashboard for all activity at a glance. See total new clients in queue, policy status, total metrics on premium placed, etc, be able to drill down by RIA, by carrier. by product (PPA vs. PPLI) , and commissions earned etc. They can drill down to the policy level specifics, but also extract the information into a report for further analysis. | x | x | x | V0: handle at high level; add sophistication and drill down into V1. and full integration into app with V2'
15 | Enable broker to jot down key notes on client / RIA interaction and get a nudge for action or alerts for staff. | x | x | x | V0: handle simplistically initially; add sophistication and drill down into V1. and full integration into app with V2' | *
16 | Ensure broker is licensed to sell in the state where sale is being contemplated, and appointed in good standing with carrier chosen. Otherwise, the broker cannot use the system to place business. | x |  |  | v0: simple look up licensing check at first; v1 and v2 add more integration and sophistication | *